## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Sprint 1 | Sprint 1 | US-001 | As a developer, I want to upload bug reports through a web interface. | MUST HAVE | None | Sonali | 3- Completed
Sprint 1 | Sprint 1 | US-002 | As a developer, I want uploaded bug reports to be preprocessed automatically. | MUST HAVE | US-001 | Sonali | 3- Completed
Sprint 1 | Sprint 2 | US-003 | As a developer, I want the system to retrieve similar historical bugs using RAG. | MUST HAVE | US-002 | Sonali | 3- Completed
Sprint 2 | Sprint 2 | US-004 | As a developer, I want AI to classify severity, priority and component. | MUST HAVE | US-003 | Sonali | 3- Completed
Sprint 2 | Sprint 2 | US-005 | As a developer, I want stack traces analyzed automatically. | MUST HAVE | US-004 | Sonali | 3- Completed
Sprint 2 | Sprint 2 | US-006 | As a developer, I want both AI agents to execute together. | MUST HAVE | US-004,US-005 | Sonali | 3- Completed
Sprint 2 | Sprint 2 | US-007 | As a developer, I want a downloadable PDF analysis report. | SHOULD HAVE | US-006 | Sonali | 3- Completed
Sprint 2 | Sprint 2 | US-008 | As a developer, I want validation results for AI agents. | MUST HAVE | US-006 | Sonali | 3- Completed
Sprint 3 | Sprint 3 | US-009 | As a developer, I want root cause analysis so that likely causes of defects can be identified using historical evidence. | MUST HAVE | US-003,US-005 | Sonali Kothapalli | 3- Completed
Sprint 3 | Sprint 3 | US-010 | As a developer, I want duplicate defect detection so that previously reported similar issues can be identified. | MUST HAVE | US-003,US-009 | Sonali Kothapalli | 3- Completed
Sprint 3 | Sprint 3 | US-011 | As a developer, I want remediation recommendations so that the system can suggest fixes and best practices. | MUST HAVE | US-009,US-010 | Sonali Kothapalli | 3- Completed
Sprint 3 | Sprint 3 | US-012 | As a developer, I want structured findings so that triage, log analysis, root cause, duplicates and remediation are displayed together. | MUST HAVE | US-004,US-005,US-009,US-010,US-011 | Sonali Kothapalli | 3- Completed
Sprint 4 | Sprint 4 | US-013 | As a developer, I want completed bug analyses stored so that defect history can be used for analytics. | MUST HAVE | US-012 | Sonali Kothapalli | 3- Completed
Sprint 4 | Sprint 4 | US-014 | As a developer, I want defect pattern analytics so that recurring themes, affected components and systemic patterns can be identified. | MUST HAVE | US-013 | Sonali Kothapalli | 3- Completed
Sprint 4 | Sprint 4 | US-015 | As a developer, I want confirmed resolved bugs added to the knowledge base so that future defects can retrieve resolved historical fixes. | MUST HAVE | US-013,US-014 | Sonali Kothapalli | 3- Completed
Sprint 4 | Sprint 4 | US-016 | As a developer, I want end-to-end testing with multiple bug types so that the complete AI bug diagnosis pipeline can be validated. | MUST HAVE | US-012,US-014,US-015 | Sonali Kothapalli | 3- Completed
Note on F1: Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 121 | 45 | 24 | 5 | 4 | 6 | 2 | 3 | 4 | 3 | 3 | 6 | 4 | 7 | 4
SPRINT 1 BACKLOG
US-001 | T1 | Create project structure | 2026-07-05 | 2026-07-05 | Sonali Kothapalli | Coding | 3- Completed | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | T2 | Develop FastAPI backend | 2026-07-05 | 2026-07-06 | Sonali Kothapalli | Design | 3- Completed | 6 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-002 | T3 | Develop bug upload module | 2026-07-06 | 2026-07-07 | Sonali Kothapalli | Build | 3- Completed | 4 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-003 | T4 | Implement preprocessing | 2026-07-07 | 2026-07-08 | Sonali Kothapalli | Design | 3- Completed | 5 | 0 | 0 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-003 | T5 | Generate embeddings | 2026-07-08 | 2026-07-09 | Sonali Kothapalli | Regression Test | 3- Completed | 5 | 0 | 0 | 0 | 2 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-003 | T6 | Build vector database | 2026-07-09 | 2026-07-10 | Sonali Kothapalli | Build | 3- Completed | 5 | 0 | 0 | 0 | 0 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-003 | T7 | Implement RAG retrieval | 2026-07-10 | 2026-07-13 | Sonali Kothapalli | Coding | 3- Completed | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 2 | 2 | 1 | 0 | 0 | 0 | 0
US-004 | T8 | Develop Triage Agent | 2026-07-13 | 2026-07-15 | Sonali Kothapalli | Design | 3- Completed | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 2 | 1 | 1 | 0 | 0
US-005 | T9 | Develop Log Analysis Agent | 2026-07-15 | 2026-07-17 | Sonali Kothapalli | Design | 3- Completed | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 1 | 1 | 0
US-006 | T10 | Implement Multi-Agent Orchestrator | 2026-07-17 | 2026-07-18 | Sonali Kothapalli | Integration Test | 3- Completed | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 0
US-007 | T11 | Generate PDF report | 2026-07-18 | 2026-07-19 | Sonali Kothapalli | Integration Test | 3- Completed | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2
US-008 | T12 | Validate agents & GitHub deployment | 2026-07-19 | 2026-07-21 | Sonali Kothapalli | Others | 2- In Progress | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2
SPRINT 3 BACKLOG
US-009 | T13 | Develop Root Cause Agent | 2026-08-01 | 2026-08-02 | Sonali Kothapalli | Coding | 3- Completed | 6 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-010 | T14 | Develop Duplicate Detection Agent | 2026-08-02 | 2026-08-03 | Sonali Kothapalli | Coding | 3- Completed | 5 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-011 | T15 | Develop Remediation Agent | 2026-08-03 | 2026-08-04 | Sonali Kothapalli | Coding | 3- Completed | 6 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-012 | T16 | Integrate structured findings dashboard | 2026-08-04 | 2026-08-05 | Sonali Kothapalli | Integration Test | 3- Completed | 6 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-012 | T17 | Validate root cause, duplicate and remediation outputs | 2026-08-05 | 2026-08-06 | Sonali Kothapalli | Regression Test | 3- Completed | 5 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 4 BACKLOG
US-013 | T18 | Implement analysis history storage | 2026-09-08 | 2026-09-08 | Sonali Kothapalli | Coding | 3- Completed | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-014 | T19 | Implement defect pattern analytics module | 2026-09-08 | 2026-09-09 | Sonali Kothapalli | Coding | 3- Completed | 6 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-014 | T20 | Add analytics API and frontend dashboard | 2026-09-09 | 2026-09-09 | Sonali Kothapalli | Integration Test | 3- Completed | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-015 | T21 | Implement resolved-bug knowledge base growth | 2026-09-09 | 2026-09-10 | Sonali Kothapalli | Coding | 3- Completed | 6 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-015 | T22 | Verify resolved bug retrieval from vector store | 2026-09-21 | 2026-09-21 | Sonali Kothapalli | Regression Test | 3- Completed | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-016 | T23 | Run five distinct end-to-end bug scenarios | 2026-09-23 | 2026-09-23 | Sonali Kothapalli | Integration Test | 3- Completed | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note: Sprint 3 dates are documentation dates used to organize the completed Milestone 3 work; Sprint 4 dates reflect the Milestone 4 work recorded during September 8–10, 2026.
Note on D2: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on E2: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on I3: This is the total task estimated in hours for all the user stories
Note on J3: Pending effort hours after completion of day 1 work
Note on K3: Pending effort hours after completion of day 2 work
Note on L3: Pending effort hours after completion of day 3 work
Note on M3: Pending effort hours after completion of day 4 work
Note on N3: Pending effort hours after completion of day 5 work
Note on O3: Pending effort hours after completion of day 6 work
Note on P3: Pending effort hours after completion of day 7 work
Note on Q3: Pending effort hours after completion of day 8 work
Note on R3: Pending effort hours after completion of day 9 work
Note on S3: Pending effort hours after completion of day 10 work
Note on T3: Pending effort hours after completion of day 11 work
Note on U3: Pending effort hours after completion of day 12 work
Note on V3: Pending effort hours after completion of day 13 work
Note on W3: Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 2 | Knowledge base preparation failed due to dataset formatting. | Cleaned dataset and generated processed bug records.
Sprint 1 | Day 4 | Frontend couldn't communicate with backend API | Corrected API routes and enabled CORS.
Sprint 1 | Day 6 | Vector database indexing issue. | Rebuilt embeddings and recreated vector database.
Sprint 1 | Day 8 | Large bug report processing was slow. | Optimized preprocessing and chunk generation.
Sprint 1 | Day 10 | Retrieval results were inaccurate. | Improved embedding generation and retrieval parameters.
Sprint 2 | Day 2 | Severity prediction inconsistent. | Improved Triage Agent rules and confidence calculation.
Sprint 2 | Day 4 | Stack traces were not parsed correctly. | Enhanced Log Analysis Agent parsing logic.
Sprint 2 | Day 6 | Multi-agent integration failed initially. | Implemented orchestrator to coordinate both agents.
Sprint 2 | Day 8 | GitHub rejected dataset larger than 100 MB. | Removed dataset from Git tracking and updated .gitignore.
Sprint 2 | Day 10 | Validation accuracy required improvement. | Validated agents using seeded dataset and updated rules.
Sprint 3 | Day 2 | Root Cause Agent produced weak hypotheses when historical evidence was limited. | Connected root cause reasoning to retrieved historical matches and component/exception information.
Sprint 3 | Day 4 | Duplicate detection required better handling of historical similarity. | Used historical matches and structured duplicate comparison to surface likely duplicates.
Sprint 3 | Day 6 | Remediation recommendations needed to be tied to root-cause evidence. | Integrated root cause, triage, log analysis and duplicate findings into remediation.
Sprint 3 | Day 8 | Milestone 3 dashboard needed to display all agent findings clearly. | Added structured findings for root cause, duplicate detection and recommended remediation.
Sprint 4 | Day 2 | Analysis history was not initially visible after testing. | Verified save_analysis integration and confirmed data/analysis_history.json was populated.
Sprint 4 | Day 4 | Analytics initially had limited structured history. | Submitted additional distinct bug scenarios and verified recurring patterns and systemic issues.
Sprint 4 | Day 6 | Resolved bugs needed to become searchable by future submissions. | Implemented resolved-bug embedding and vector-store upsert and verified M4-001 retrieval.
Sprint 4 | Day 8 | PowerShell JSON submission syntax caused curl parsing errors. | Used Invoke-RestMethod with a PowerShell hashtable converted to JSON.
Sprint 4 | Day 10 | Final validation required multiple distinct bug types. | Executed five end-to-end scenarios covering PDF Viewer, database, authentication, API and UI issues.

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | 2026-07-05 | 2026-07-12 | Sonali Kothapalli | Develop modular backend APIs and RAG pipeline | Hardcoding sample bug reports | Testing each module independently | Completed bug upload, preprocessing, embeddings, vector store and RAG retrieval
2 | Sprint 2 | 2026-07-13 | 2026-07-21 | Sonali Kothapalli | Develop AI agents and automate analysis | Manual bug classification | Improving agent accuracy and integration testing | Implemented Triage Agent, Log Analysis Agent, orchestration, validation and PDF report generation
3 | Sprint 3 | 2026-08-01 | 2026-08-07 | Sonali Kothapalli | Use historical evidence more strongly in root cause and duplicate analysis. | Relying on generic recommendations without evidence. | Modular agent design and integration testing. | Completed Root Cause Agent, Duplicate Detection Agent, Remediation Agent and structured findings dashboard.
4 | Sprint 4 | 2026-09-08 | 2026-09-10 | Sonali Kothapalli | Automate analytics and knowledge-base feedback from completed bugs. | Manual tracking of resolved defects for future reuse. | Testing the full pipeline with varied defect scenarios. | Completed analysis history, defect analytics, analytics dashboard, resolved-bug knowledge-base growth and five end-to-end tests.
5
6
7
Note: Sprint 3 dates are documentation dates used to organize the completed Milestone 3 work; Sprint 4 dates reflect the Milestone 4 work recorded during September 8–10, 2026.