## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Sonali Kothapalli | 2026-07-08 | Uploaded bug reports were not stored correctly. | Sprint 1 | Sonali | Logical | Fixed upload API | 2026-07-08 | Closed | Verified
2 | Sonali Kothapalli | 2026-07-10 | Vector database retrieval returned incorrect matches. | Sprint 1 | Sonali | Maintainability | Regenerated embeddings. | 2026-07-10 | Closed | Resolved
3 | Sonali Kothapalli | 2026-07-15 | Triage Agent predicted incorrect priority. | Sprint 2 | Sonali | User Interface | Updated prediction rules. | 2026-07-16 | Closed | Accuracy improved
4 | Sonali Kothapalli | 2026-07-17 | Stack trace parser missed exception information. | Sprint 2 | Sonali | Logical | Improved parsing logic. | 2026-07-17 | Closed | Verified
5 | Sonali Kothapalli | 2026-07-19 | GitHub rejected dataset larger than 100 MB. | Sprint 2 | Sonali | Maintainability | Removed dataset from Git and updated .gitignore. | 2026-07-19 | Closed | Successfully pushed project
6 | Sonali Kothapalli | 2026-08-01 | Root Cause Agent sometimes produced a weak or insufficiently grounded root-cause hypothesis. | Sprint 3 | Sonali | Logical | Improved root-cause reasoning using retrieved historical evidence and log-analysis findings. | 2026-08-02 | Closed | Validated in structured findings.
7 | Sonali Kothapalli | 2026-08-03 | Duplicate Detection Agent needed better handling of similarity scores and historical bug details. | Sprint 3 | Sonali | Logical | Refined duplicate matching output and included similarity, status, and resolution information. | 2026-08-04 | Closed | Verified with historical matches.
8 | Sonali Kothapalli | 2026-08-05 | Remediation Agent recommendations were not sufficiently grounded in retrieved bug evidence. | Sprint 3 | Sonali | Logical | Grounded recommended fixes using historical matches, root-cause findings, and actionable steps. | 2026-08-06 | Closed | Recommendation card verified.
9 | Sonali Kothapalli | 2026-09-09 | Analysis history was created but was initially difficult to verify because the history JSON file was not immediately visible. | Sprint 4 | Sonali | Maintainability | Verified the data directory and confirmed analysis_history.json was being created and updated. | 2026-09-09 | Closed | History storage verified.
10 | Sonali Kothapalli | 2026-09-21 | Knowledge-base testing using a JSON request in PowerShell caused request-body syntax issues. | Sprint 4 | Sonali | Logical | Corrected the PowerShell request syntax and successfully added a resolved bug to the knowledge base. | 2026-09-23 | Closed | M4-001 successfully stored and retrieved.
11 | Sonali Kothapalli | 2026-09-23 | Knowledge-base vector insertion required safe handling when a resolved bug used an existing chunk identifier. | Sprint 4 | Sonali | Maintainability | Changed the ChromaDB insertion behavior to upsert so resolved knowledge can be added or updated safely. | 2026-09-23 | Closed | Resolved bug became searchable through RAG.

## Sheet2
Logical
User Interface
Maintainability
Standards
Others