## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Sonali Kothapalli | 2026-07-08 | Uploaded bug reports were not stored correctly. | Sprint 1 | Sonali | Logical | Fixed upload API | 2026-07-08 | Closed | Verified
2 | Sonali Kothapalli | 2026-07-10 | Vector database retrieval returned incorrect matches. | Sprint 1 | Sonali | Maintainability | Regenerated embeddings. | 2026-07-10 | Closed | Resolved
3 | Sonali Kothapalli | 2026-07-15 | Triage Agent predicted incorrect priority. | Sprint 2 | Sonali | User Interface | Updated prediction rules. | 2026-07-16 | Closed | Accuracy improved
4 | Sonali Kothapalli | 2026-07-17 | Stack trace parser missed exception information. | Sprint 2 | Sonali | Logical | Improved parsing logic. | 2026-07-17 | Closed | Verified
5 | Sonali Kothapalli | 2026-07-19 | GitHub rejected dataset larger than 100 MB. | Sprint 2 | Sonali | Maintainability | Removed dataset from Git and updated .gitignore. | 2026-07-19 | Closed | Successfully pushed project

## Sheet2
Logical
User Interface
Maintainability
Standards
Others